Launch Roadmap — From Repo to Revenue

Companion to the Business Plan. Sequenced for a solo founder; calendar assumes part-time effort. Dates are targets from June 2026.

# Phase 0 — Foundation (June–July 2026, weeks 1–4)

- Rename. Pick a trademark-clear, pronounceable name; screen via USPTO TESS, buy the .com/.app. Everything downstream (cert, site, installer) uses the new name, so this is genuinely first.

- Harden security: finish argon2 password hashing + HTTPS for WAN exposure; default LAN-only; write SECURITY.md and a responsible-disclosure address. Do not launch a surveillance product without this.

- Validate the cross-platform claim: build and test on an Apple Silicon Mac (CoreML EP) and a Linux/CUDA box. If macOS slips, launch Windows-first and say so honestly.

- Code signing: buy a Windows Authenticode certificate (SmartScreen otherwise blocks the NSIS installer) and join the Apple Developer Program ($99/yr) for notarized macOS builds.

- Webcam-validate the live browser features that shipped build-green but unvalidated: gesture overlay, polygon zone editor, touchless PTZ.

# Phase 1 — Sellable Product (July–August 2026, weeks 5–8)

- Licensing infrastructure: Lemon Squeezy account, $79 product + $29/yr update plan, license-key issuance via their API; add key activation (2 machines) + offline grace to the app. Keep the check local-friendly — never brick a camera system because a license server is unreachable.

- Trial mode: 30-day full-featured trial with a clean in-app upgrade path.

- Website: landing page (positioning sentence + 90-second demo video), docs site, compatibility list, download links. The demo video is the highest-leverage marketing asset — show CLIP search and the duress gesture.

- Crash/error reporting (opt-in) so beta issues are diagnosable.

- Auto-update channel for the desktop app — shipping fixes fast is the indie superpower.

# Phase 2 — Private Beta (August–September 2026, weeks 9–14)

- Recruit 50–100 testers from IP Cam Talk, r/BlueIris, r/selfhosted, Home Assistant forums; free founder licenses for actionable reports.

- Stand up a Discord (support + community) and a public issue tracker.

- Build the camera-compatibility matrix from real beta hardware; fix the top-10 pain points.

- Pricing validation: survey beta users on willingness to pay before locking $79.

- Line up 3–5 YouTube reviewers under embargo; ship them licenses + a press kit.

# Phase 3 — Public Launch (October 2026)

- Coordinated: reviewer embargo lifts + Show HN + Product Hunt + posts in the communities that supplied beta testers, same week.

- Founder pricing $59 for the first 500 licenses, then $79.

- Be terminally online for launch week: HN comments, Reddit threads, Discord. Responsiveness is the review.

# Phase 4 — Post-launch (Q4 2026 →)

- Ship visibly every 2–4 weeks; publish a public roadmap.

- SEO content: 'Blue Iris alternative for Mac', 'Frigate without Docker', migration guides.

- Year-2 revenue layers: update-plan renewals; optional cloud relay subscription (~$4–5/mo) for zero-config remote access.

- Reassess open-sourcing non-differentiating components (e.g. the gesture crate) as marketing.

# Budget (cash needed before first revenue)

| Item | Cost | When |
| --- | --- | --- |
| Domain + trademark screening | $50–500 | Phase 0 |
| Windows code-signing cert | $200–400/yr | Phase 0 |
| Apple Developer Program | $99/yr | Phase 0 |
| Site + docs hosting | $0–20/mo | Phase 1 |
| Test cameras (2–3 extra brands) | $200–400 | Phase 2 |
| External auth/security review | $500–2,000 | Phase 2 |
| Total | ≈ $1,100–3,500 |  |

Kill criteria worth writing down now: if the beta cohort converts below ~10% at $59, or support load exceeds what evenings can absorb at 100 users, revisit pricing, scope, or the solo-founder assumption before public launch.